## Small_SAAS -- 2020 Release
SMALL - FEATURE LIST Release December 2019 - September 2020
PROJECT TITLE : Small SAAS Features
PROJECT MANAGER : Rajesh Rajaram
COMPANY NAME : AuctionSoftware
| Dec - 19 1st Week |  |  |  |  | Dec - 19 2nd Week |  |  |  |  | Dec - 19 3rd Week |  |  |  |  | Dec - 19 4th Week |  |  |  |  | Jan -20 1st Week |  |  |  |  | Jan -20 2nd Week |  |  |  |  | Jan -20 3rd Week |  |  |  |  | Jan -20 4th Week |  |  |  |  | Feb -20 1st Week |  |  |  |  | Feb -20 2nd Week |  |  |  |  | Feb -20 3rd Week |  |  |  |  | Feb -20 4th Week |  |  |  |  | March -20 1st Week |  |  |  |  | March -20 2nd Week |  |  |  |  | March -20 3rd Week |  |  |  |  | March -20 4th Week |  |  |  |  | April -20 1st Week |  |  |  |  | April -20 2nd Week |  |  |  |  | April -20 3rd Week |  |  |  |  | April -20 4th Week |  |  |  |  | May -20 1st Week |  |  |  |  | May -20 2nd Week |  |  |  |  | May -20 3rd Week |  |  |  |  | May -20 4th Week |  |  |  |  | June -20 1st Week |  |  |  |  | June -20 2nd Week |  |  |  |  | June -20 3rd Week |  |  |  |  | June -20 4th Week |  |  |  |  | July -20 1st Week |  |  |  |  | July -20 2nd Week |  |  |  |  | July -20 3rd Week |  |  |  |  | July -20 4th Week |  |  |  |  | August -20 1st Week |  |  |  |  | August -20 2nd Week |  |  |  |  | August -20 3rd Week |  |  |  |  | August -20 4th Week |  |  |  |  | September - 20 1st Week |  |  |  |  | September- 20 2nd Week |  |  |  |  | September- 20 3rd Week |  |  |  |  | September- 20 4th Week
| M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
Event Management | bar: Dec - 19 1st Week M to Dec - 19 1st Week F; March -20 1st Week M
Event Theme | bar: Dec - 19 1st Week M
View Event | bar: Dec - 19 1st Week M
Event customer (View customer purchase, My customer list, Add customer) | bar: Dec - 19 1st Week T to Dec - 19 1st Week T
Event Analytics | bar: Dec - 19 1st Week F; Dec - 19 2nd Week T to Dec - 19 2nd Week W
Bid sheet priview and print bid sheet | bar: Dec - 19 2nd Week M; Dec - 19 2nd Week W
Leaderboard | bar: Dec - 19 2nd Week F
Donor Management | bar: Dec - 19 2nd Week M to Dec - 19 2nd Week F
Add Donor | bar: Dec - 19 2nd Week M
Manage Donor | bar: Dec - 19 2nd Week M to Dec - 19 2nd Week T
Import | bar: Dec - 19 2nd Week W
Export | bar: Dec - 19 2nd Week W
Donate here | bar: Dec - 19 3rd Week M to Dec - 19 3rd Week T
Advertise management | bar: Dec - 19 2nd Week F
Dashboard | bar: Dec - 19 3rd Week M to Dec - 19 3rd Week F
Watch list | bar: Dec - 19 3rd Week M
My Orders | bar: Dec - 19 3rd Week M
Feedback | bar: Dec - 19 4th Week T to Dec - 19 4th Week F
Setting (Profile-User Info, Shipping details and Store location) | bar: Dec - 19 3rd Week T to Dec - 19 3rd Week W
Photo uploader | bar: Dec - 19 3rd Week W to Dec - 19 3rd Week T
Create discount | bar: Dec - 19 3rd Week F to Dec - 19 4th Week M
Product view page | bar: Dec - 19 3rd Week F
FAQs | bar: Dec - 19 4th Week T
Invoice | bar: Dec - 19 4th Week M; Dec - 19 4th Week W
Deposit fund | bar: Dec - 19 4th Week T to Dec - 19 4th Week F
Checkout process | bar: Dec - 19 4th Week M to Jan -20 1st Week F
Add to cart | bar: Jan -20 1st Week M
Product view | bar: Jan -20 1st Week T
Similar products | bar: Jan -20 1st Week T to Jan -20 1st Week F
Bidding and buy now -Reserve price | bar: Jan -20 1st Week W to Jan -20 1st Week F
Timer and bid history | bar: Jan -20 1st Week W to Jan -20 1st Week F
Paypal and credit card checkout
Shipping options | bar: Jan -20 1st Week T
Buyer dashboard (Active, Won and lost)
Saved Shipping address and Add new shipping | bar: Jan -20 1st Week F
My Dashboard -View Stores | bar: Jan -20 2nd Week M to Jan -20 3rd Week F
Manage store | bar: Jan -20 2nd Week T to Jan -20 2nd Week W; Jan -20 3rd Week T
Store list | bar: Jan -20 2nd Week T; Jan -20 3rd Week W
My Marketplace | bar: Jan -20 2nd Week W; Jan -20 3rd Week W to Jan -20 3rd Week T
Edit Marketplace | bar: Jan -20 2nd Week T; Jan -20 3rd Week T to Jan -20 3rd Week W
Edit category | bar: Jan -20 2nd Week F; Jan -20 3rd Week F
View Market place | bar: Jan -20 4th Week M
Buyer APP: The APP provides and easy way to auto check-in and start bidding. We do have extensive features in App like: | bar: Jan -20 4th Week M to Jan -20 4th Week F
Searching through the events | bar: Jan -20 4th Week M
Check in to the event | bar: Jan -20 4th Week T
Browse all the products for sale in the Auction | bar: Jan -20 4th Week W to Jan -20 4th Week T
Watchlist the item to get notifications | bar: Jan -20 4th Week T
Start bidding and get outbid notifications in App that helps to set the max bid so the system bids on our proxy. | bar: Jan -20 4th Week F to Feb -20 1st Week M
Add Multiple Items to cart | bar: Feb -20 1st Week T to Feb -20 1st Week W
Checkout the product by applying coupon in a single click | bar: Feb -20 1st Week T to Feb -20 2nd Week M
My purchase history shows all the purchased items | bar: Feb -20 2nd Week T to Feb -20 2nd Week W
Invoice generation | bar: Feb -20 2nd Week T to Feb -20 2nd Week F
Seller and Buyer App | bar: Feb -20 3rd Week M to Feb -20 3rd Week F
Testing and Bug fixes | bar: Feb -20 3rd Week T to March -20 1st Week F
Reseller Web | bar: March -20 2nd Week M to March -20 2nd Week F
Reseller License Fee pay to AuctionSoftware | bar: March -20 2nd Week M to March -20 2nd Week T; March -20 3rd Week F
Reseller home page need to allow seller registration | bar: March -20 2nd Week W to March -20 2nd Week T; March -20 3rd Week M; March -20 3rd Week T
Seller of Reseller will need to register seller membership | bar: March -20 3rd Week W
Reseller can suspend or remove their seller | bar: March -20 2nd Week T to March -20 2nd Week T; March -20 3rd Week M to March -20 3rd Week T
Reseller Store Surcharge on top of standard seller membership | bar: March -20 3rd Week W to March -20 3rd Week T
Reseller Store Transaction Surcharge % on top of 1% member transaction fee | bar: March -20 2nd Week T to March -20 2nd Week F; March -20 3rd Week T to March -20 3rd Week W
Reseller can create product inventory | bar: March -20 2nd Week M to March -20 2nd Week T
Inventory product add or remove | bar: March -20 4th Week M to March -20 4th Week T
Inventory product reserve price | bar: March -20 4th Week W to March -20 4th Week T
inventory product of auction or buy-now | bar: March -20 4th Week F to April -20 1st Week M
Only Seller of Reseller can access to the inventory | bar: March -20 4th Week W to March -20 4th Week T
Seller can pull the inventory product and post on their store | bar: April -20 1st Week M to April -20 1st Week T
Seller cannot alter the inventory product title, description, and quantity, etc. but only the Store reserve price for auction or buy-now. The Store price should higher than Reseller reserve price set by Reseller. | bar: April -20 2nd Week M to April -20 2nd Week F
Seller follow the same rule that auction is for whole quantity of product batch. | bar: April -20 1st Week T to April -20 1st Week W; April -20 4th Week M to April -20 4th Week F
Product availability base on completion of payment process. Product need to be temporary lock during payment process. Queue up the transaction of same product when the product in the inventory is marked "PIP" Payment-In-Process. | bar: April -20 3rd Week M to April -20 3rd Week F
Ticketing system | bar: May -20 1st Week M to May -20 1st Week F
Event Ticket Only We can create an event where we can Just users register and book their Tickets for the Event. | bar: May -20 1st Week T to May -20 2nd Week F
Event with Seating Ticket We also have a option where the event Admin can define the Seating Arrangements of the Tickets for the Event | bar: May -20 3rd Week M to June -20 1st Week T
Adding categories for The Ticket layout | bar: June -20 1st Week W to June -20 1st Week F
Other Features | bar: June -20 2nd Week M to June -20 2nd Week F
Bidder number generation - auto and manual | bar: June -20 2nd Week T to June -20 2nd Week T
Attendance check in – via mobile app | bar: June -20 2nd Week T to June -20 3rd Week M
Table seating and on event day seating assignment | bar: June -20 2nd Week F to June -20 3rd Week T
Silent auction - online and event day bidding (mobile and bidder sheets) | bar: June -20 3rd Week W to June -20 4th Week T
Silent auction item intake - items donated, quantity | bar: June -20 4th Week W to June -20 4th Week F
Auction basket creation grouping of items (lot auctions) | bar: June -20 4th Week W; June -20 4th Week F
Live auctions (mostly nonprofits) | bar: June -20 4th Week W
Paddle raises - mobile and manual – Partial | bar: June -20 4th Week F to July -20 1st Week T
Auto check out for end of event day | bar: July -20 1st Week W to July -20 1st Week T
Receipt generation - electronic and printed | bar: July -20 2nd Week T to July -20 2nd Week F
Marketplace for nonprofits to trade left over auction items | bar: July -20 3rd Week M to July -20 3rd Week W; July -20 4th Week T
Live streaming of live auctions | bar: July -20 1st Week F to July -20 2nd Week M; July -20 3rd Week F to July -20 4th Week T
Shipping integration and status notifications | bar: July -20 4th Week W to July -20 4th Week F
Testing | bar: August -20 1st Week M to August -20 1st Week F
Manual Testing | bar: August -20 1st Week M to August -20 1st Week F; August -20 2nd Week W to August -20 2nd Week F; August -20 4th Week M to August -20 4th Week F
Mass Testing | bar: August -20 2nd Week M to August -20 2nd Week T; August -20 3rd Week W to August -20 3rd Week T
Automation Testing | bar: August -20 2nd Week W to August -20 3rd Week M; August -20 4th Week W to August -20 4th Week T
Load Testing | bar: August -20 3rd Week M to August -20 3rd Week T
Penetration /Security Testing | bar: August -20 3rd Week F to August -20 4th Week F
Beta Testing & Delivery | bar: September - 20 1st Week M to September- 20 4th Week F

## Medium_CH -- 2020 Release
MEDIUM - FEATURE LIST Release October 2019 - September 2020
PROJECT TITLE : Medium Control Features
PROJECT MANAGER : Rajesh Rajaram
COMPANY NAME : AuctionSoftware
| Oct -19 1st WK |  |  |  |  | Oct- 19 2nd WK |  |  |  |  | Oct- 19 3rd WK |  |  |  |  | Oct- 19 4th WK |  |  |  |  | Nov-19 1st WK |  |  |  |  | Nov- 19 2nd WK |  |  |  |  | Nov- 19 3rd WK |  |  |  |  | Nov- 19 4th WK |  |  |  |  | Dec-19 1st WK |  |  |  |  | Dec- 19 2nd WK |  |  |  |  | Dec- 19 3rd WK |  |  |  |  | Dec- 19 4th WK |  |  |  |  | Jan-20 1st WK |  |  |  |  | Jan-20 2nd WK |  |  |  |  | Jan-20 3rd WK |  |  |  |  | Jan-20 4th WK |  |  |  |  | Feb-20 1st WK |  |  |  |  | Feb-20 2nd WK |  |  |  |  | Feb-20 3rd WK |  |  |  |  | Feb-20 4th WK |  |  |  |  | March-20 1st WK |  |  |  |  | March-20 2nd WK |  |  |  |  | March-20 3rd WK |  |  |  |  | March-20 4th WK |  |  |  |  | April-20 1st WK |  |  |  |  | April-20 2nd WK |  |  |  |  | April-20 3rd WK |  |  |  |  | April-20 4th WK |  |  |  |  | May-20 1st WK |  |  |  |  | May-20 2nd WK |  |  |  |  | May-20 3rd WK |  |  |  |  | May-20 4th WK |  |  |  |  | June-20 1st WK |  |  |  |  | Jne-20 2nd WK |  |  |  |  | June-20 3rd WK |  |  |  |  | June-20 4th WK |  |  |  |  | July-20 1st WK |  |  |  |  | July-20 2nd WK |  |  |  |  | July-20 3rd WK |  |  |  |  | July-20 4th WK |  |  |  |  | Aug-20 1st WK |  |  |  |  | Aug-20 2nd WK |  |  |  |  | Aug-20 3rd WK |  |  |  |  | Aug-20 4th WK |  |  |  |  | Sep-20 1st WK |  |  |  |  | Sep-20 2nd WK |  |  |  |  | Sep-20 3rd WK |  |  |  |  | Sep-20 4th WK |  |  |  |  | Oct-20 1st WK |  |  |  |  | Oct-20 2nd WK |  |  |  |  | Oct-20 3rd WK |  |  |  |  | Oct-20 4th WK |  |  |  |  | Nov-20 1st WK |  |  |  |  | Nov-20 2nd WK |  |  |  |  | Nov-20 3rd WK |  |  |  |  | Nov-20 4th WK |  |  |  |  | Dec-20 1st WK |  |  |  |  | Dec-20 2nd WK |  |  |  |  | Dec-20 3rd WK |  |  |  |  | Dec-20 4th WK
| M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
Authentication API | bar: Oct -19 1st WK M to Oct -19 1st WK F
Registration | bar: Oct -19 1st WK M
Login | bar: Oct -19 1st WK M
Forgot Password | bar: Oct -19 1st WK T
Chek Email Exist | bar: Oct -19 1st WK T
Home page API | bar: Oct -19 1st WK W to Oct- 19 2nd WK M
Search | bar: Oct -19 1st WK M to Oct -19 1st WK W; Oct- 19 2nd WK M
Product View Page without Login | bar: Oct -19 1st WK W; Oct- 19 2nd WK M to Oct- 19 2nd WK W
Product View Page with Login | bar: Oct- 19 2nd WK T to Oct- 19 2nd WK W
Request Shipping Price | bar: Oct- 19 2nd WK W to Oct- 19 2nd WK F
Get Watchlist Product | bar: Oct- 19 2nd WK T to Oct- 19 3rd WK M
Add Product To Watchlist | bar: Oct- 19 2nd WK T to Oct- 19 3rd WK W
Remove Product From Watchlist | bar: Oct- 19 2nd WK T; Oct- 19 3rd WK W to Oct- 19 3rd WK F
Bidding API | bar: Oct- 19 2nd WK T to Oct- 19 2nd WK F; Oct- 19 3rd WK W to Oct- 19 3rd WK T
Check Bid Eligible | bar: Oct- 19 3rd WK W to Oct- 19 4th WK T
Bidding API | bar: Oct- 19 3rd WK M to Oct- 19 3rd WK T; Oct- 19 4th WK T to Oct- 19 4th WK T
Bid History | bar: Oct- 19 4th WK T to Oct- 19 4th WK F
Profile API | bar: Oct- 19 3rd WK W to Oct- 19 3rd WK F; Oct- 19 4th WK W
Get Profile Details | bar: Oct- 19 4th WK M; Oct- 19 4th WK W to Nov-19 1st WK T
Update Shipping Address | bar: Nov-19 1st WK M to Nov-19 1st WK T
Update Shipping Phone Number | bar: Nov-19 1st WK W to Nov- 19 2nd WK T
Change Password | bar: Nov- 19 2nd WK T to Nov- 19 3rd WK M
Edit Notification Settings | bar: Nov- 19 2nd WK T to Nov- 19 2nd WK W; Nov- 19 3rd WK T to Nov- 19 3rd WK F
Buyer Dashboard API | bar: Nov- 19 3rd WK T to Nov- 19 3rd WK W; Nov- 19 4th WK M to Nov- 19 4th WK T
Buyer Dashboard Count | bar: Nov- 19 4th WK T to Nov- 19 4th WK W
Items Won | bar: Nov- 19 4th WK W
Items Lost | bar: Nov- 19 4th WK W to Nov- 19 4th WK F
Get Saved Search List | bar: Nov- 19 4th WK F to Dec-19 1st WK W
Save Search | bar: Dec-19 1st WK W to Dec-19 1st WK F
Remove Saved Search | bar: Dec-19 1st WK T to Dec-19 1st WK F
Checkout API | bar: Dec-19 1st WK W; Dec- 19 2nd WK M to Dec- 19 2nd WK W
Get Invoice ID | bar: Dec-19 1st WK T to Dec-19 1st WK F; Dec- 19 2nd WK T to Dec- 19 2nd WK W
Check Invoice | bar: Dec- 19 2nd WK W to Dec- 19 2nd WK F
Get Invoice Details | bar: Dec- 19 2nd WK F to Dec- 19 3rd WK T; Dec- 19 3rd WK T to Dec- 19 3rd WK F
Update Shipping Address At Checkout | bar: Dec- 19 3rd WK T to Dec- 19 3rd WK T; Dec- 19 4th WK M
Remove Unselected Product For Checkout for Shipping | bar: Dec- 19 4th WK M to Dec- 19 4th WK W
Remove Unselected Product For Checkout for Local Shipping | bar: Dec- 19 4th WK T
Remove All Shipping Fee | bar: Dec- 19 4th WK W to Jan-20 1st WK T; Jan-20 1st WK T to Jan-20 1st WK F
Concept NRSCA | bar: Jan-20 1st WK T to Jan-20 1st WK W
Update Freight Request | bar: Jan-20 1st WK W; Jan-20 2nd WK M to Jan-20 2nd WK T; Jan-20 2nd WK F
Pay with Paypal | bar: Jan-20 1st WK W to Jan-20 1st WK F; Jan-20 2nd WK T; Jan-20 2nd WK T
Pay full Amount with Use Credit | bar: Jan-20 2nd WK T to Jan-20 2nd WK W; Jan-20 3rd WK M to Jan-20 3rd WK W
Pay using Use Credit and remaining with Credit Card or Paypal | bar: Jan-20 2nd WK W to Jan-20 2nd WK F; Jan-20 3rd WK T to Jan-20 3rd WK T
Seller Dashboard API | bar: Jan-20 3rd WK W
Seller Dashboard Counts | bar: Jan-20 3rd WK T to Jan-20 3rd WK F; Jan-20 4th WK T
Add New Product | bar: Jan-20 4th WK M to Jan-20 4th WK T
Pending List | bar: Jan-20 4th WK W to Jan-20 4th WK F
View Pending Product View | bar: Jan-20 4th WK T to Jan-20 4th WK F
Update Pending Product | bar: Feb-20 1st WK M to Feb-20 1st WK W
Active Products List | bar: Feb-20 1st WK W
Sold Products Listing | bar: Feb-20 1st WK M to Feb-20 1st WK T
View Balance | bar: Feb-20 1st WK T to Feb-20 1st WK W
Cashout List | bar: Feb-20 1st WK T to Feb-20 2nd WK W
Cashout | bar: Feb-20 2nd WK W to Feb-20 2nd WK T
Sales Tax | bar: Feb-20 2nd WK T to Feb-20 3rd WK M; Feb-20 3rd WK T to Feb-20 3rd WK F
Language Manager API | bar: Feb-20 2nd WK M to Feb-20 2nd WK T; Feb-20 2nd WK F to Feb-20 3rd WK T
All Languages | bar: Feb-20 3rd WK W to Feb-20 3rd WK F; Feb-20 4th WK T to Feb-20 4th WK T
Specific Language | bar: Feb-20 4th WK M; Feb-20 4th WK T
Create Variables | bar: Feb-20 4th WK T to Feb-20 4th WK T
Message API | bar: Feb-20 4th WK T to Feb-20 4th WK F
Product Message | bar: March-20 1st WK M to March-20 1st WK W
Product Message Buyer | bar: March-20 1st WK W to March-20 1st WK T; March-20 2nd WK M to March-20 2nd WK W
Product Message Seller | bar: March-20 1st WK T to March-20 1st WK F; March-20 2nd WK W to March-20 2nd WK T
Advanced API | bar: March-20 2nd WK W
Get Particular Product Details | bar: March-20 2nd WK T to March-20 3rd WK T
Create Community | bar: March-20 3rd WK T; March-20 3rd WK T to March-20 4th WK M
Add User To Community | bar: March-20 3rd WK T to March-20 3rd WK W; March-20 4th WK M to March-20 4th WK W
Create Announcement | bar: March-20 4th WK W; March-20 4th WK F
Get All Announcements | bar: March-20 4th WK W to March-20 4th WK F
Farm Details | bar: April-20 1st WK M to April-20 1st WK T
Seller Feedbacks | bar: April-20 1st WK T
Get Farm Details | bar: April-20 1st WK W to April-20 2nd WK M
Get All Products Of Seller | bar: April-20 2nd WK M to April-20 2nd WK W
Other API | bar: April-20 2nd WK W to April-20 3rd WK M
Add Comment In Discussion | bar: April-20 2nd WK W; April-20 2nd WK F to April-20 3rd WK T
Invite User To Community | bar: April-20 3rd WK T to April-20 3rd WK W
Get Lot Details | bar: April-20 3rd WK W to April-20 3rd WK F
Create Auction Slot | bar: April-20 3rd WK M to April-20 3rd WK T; April-20 4th WK M
Edit Auction Lot | bar: April-20 4th WK M to April-20 4th WK W; April-20 4th WK F
Get Edit Auction Details | bar: April-20 4th WK W to April-20 4th WK F
Add Credit Card | bar: May-20 1st WK M to May-20 1st WK W
Contact Us | bar: May-20 1st WK W to May-20 2nd WK M
View Invoice | bar: May-20 1st WK W to May-20 1st WK T; May-20 2nd WK T; May-20 2nd WK T to May-20 2nd WK F
Blog | bar: May-20 1st WK T; May-20 1st WK T; May-20 2nd WK M; May-20 2nd WK W to May-20 2nd WK T; May-20 3rd WK M to May-20 3rd WK T
Shipping | bar: May-20 2nd WK W; May-20 2nd WK F; May-20 3rd WK T; May-20 3rd WK T to May-20 3rd WK F
Save Bid Splits | bar: May-20 2nd WK M to May-20 2nd WK W; May-20 3rd WK T to May-20 3rd WK W; May-20 3rd WK F to May-20 4th WK T
Paypal | bar: May-20 4th WK M to May-20 4th WK W
Cancel Auction | bar: May-20 4th WK W; May-20 4th WK F
Update Wallet | bar: May-20 4th WK W to May-20 4th WK F
View Feedback | bar: June-20 1st WK M to June-20 1st WK W
Submit Feedback | bar: June-20 1st WK W to June-20 1st WK F
Quick Books (For Invoice) | bar: June-20 1st WK W; June-20 1st WK F to Jne-20 2nd WK M; Jne-20 2nd WK W to Jne-20 2nd WK F; June-20 3rd WK W to June-20 3rd WK T; July-20 1st WK F
Quick Books (For Products) | bar: Jne-20 2nd WK T; Jne-20 2nd WK T; June-20 3rd WK T to June-20 3rd WK F; June-20 4th WK W; July-20 1st WK F
Set Price For Refurbished Products (Admin Side) | bar: Jne-20 2nd WK T; June-20 3rd WK M; June-20 3rd WK F; June-20 4th WK T to June-20 4th WK W; July-20 1st WK T
Buyer Purchase History | bar: June-20 3rd WK F to July-20 1st WK T
Search Refurbished Product | bar: July-20 1st WK T to July-20 1st WK W; July-20 1st WK F to July-20 2nd WK F; July-20 3rd WK T
Staggered API | bar: July-20 1st WK M; July-20 1st WK W; July-20 2nd WK M to July-20 2nd WK W; July-20 2nd WK F; July-20 3rd WK W
Create | bar: July-20 1st WK M; July-20 2nd WK M to July-20 2nd WK T; July-20 2nd WK F; July-20 3rd WK W
Update | bar: July-20 2nd WK T; July-20 3rd WK W
Cart API | bar: July-20 3rd WK W to July-20 3rd WK T
Add to cart | bar: July-20 3rd WK T
Remove to cart | bar: July-20 3rd WK T to July-20 3rd WK F
View cart | bar: July-20 3rd WK F
Announcement API | bar: July-20 3rd WK F
Add Announcement | bar: July-20 4th WK M
delete Announcement | bar: July-20 4th WK T
View All Announcement | bar: July-20 3rd WK F; July-20 4th WK T; July-20 4th WK T
Extending Bidding | bar: July-20 4th WK M to July-20 4th WK T; July-20 4th WK T
Bid Increment API | bar: July-20 4th WK T to July-20 4th WK T
Category API | bar: July-20 4th WK T; July-20 4th WK F
Filter API | bar: July-20 4th WK T
Vehicle API | bar: July-20 4th WK T to Aug-20 1st WK T
Spare Parts 1.0 | bar: Aug-20 1st WK W
Registration Without Card | bar: Aug-20 1st WK T
Registration With Card | bar: Aug-20 1st WK F to Aug-20 2nd WK M
Login Save | bar: Aug-20 1st WK F to Aug-20 2nd WK M
Check Card First Time | bar: Aug-20 1st WK F; Aug-20 2nd WK T to Aug-20 2nd WK W
Insert Extra Card | bar: Aug-20 2nd WK W
Update Cart Profile | bar: Aug-20 2nd WK W to Aug-20 3rd WK M
Delete Card Pay | bar: Aug-20 3rd WK M to Aug-20 3rd WK T
Get Card Profile | bar: Aug-20 3rd WK W
Contact Us Data | bar: Aug-20 3rd WK W
Send Friendly Email | bar: Aug-20 3rd WK W to Aug-20 3rd WK F
Notify User Product is ready for pick up | bar: Aug-20 3rd WK F to Aug-20 4th WK M; Aug-20 4th WK W
Watchlist | bar: Aug-20 3rd WK F to Aug-20 4th WK W
Get US State | bar: Aug-20 4th WK M to Aug-20 4th WK W
Upcoming auctions | bar: Aug-20 3rd WK T to Aug-20 4th WK W; Aug-20 4th WK F
Recent Search With Pagination | bar: Aug-20 4th WK M; Aug-20 4th WK W to Aug-20 4th WK F
Recent Search | bar: Aug-20 4th WK M; Aug-20 4th WK T to Aug-20 4th WK F
Search | bar: Aug-20 4th WK M; Aug-20 4th WK F
Delete Saved Search | bar: Aug-20 4th WK F
Add Saved Search | bar: Aug-20 4th WK F
Get All Products | bar: Aug-20 4th WK F
Get Product Details | bar: Aug-20 4th WK F
Get Offer Details | bar: Aug-20 4th WK F
Get Settings | bar: Aug-20 4th WK F
Get All Users | bar: Aug-20 4th WK F
Update Awarded | bar: Aug-20 4th WK F
Update Bid Split Awarded | bar: Sep-20 1st WK M to Sep-20 1st WK W
Spare Parts 2.0 | bar: Sep-20 1st WK T to Sep-20 2nd WK T
Insert Paid Status for Bids | bar: Sep-20 1st WK F to Sep-20 2nd WK T
Request Shipping | bar: Sep-20 1st WK F to Sep-20 2nd WK T
Insert Shipping | bar: Sep-20 1st WK F to Sep-20 2nd WK T
Buyer Transaction | bar: Sep-20 2nd WK T
User Profile | bar: Sep-20 2nd WK T to Sep-20 2nd WK F
Update Notification | bar: Sep-20 2nd WK T; Sep-20 2nd WK F
Get Notification | bar: Sep-20 2nd WK F to Sep-20 3rd WK M
Save Category Search | bar: Sep-20 3rd WK M; Sep-20 3rd WK T
Save Tax File | bar: Sep-20 3rd WK M; Sep-20 3rd WK W; Sep-20 3rd WK F to Sep-20 4th WK M
User Wish List | bar: Sep-20 3rd WK M to Sep-20 3rd WK W; Sep-20 3rd WK F to Sep-20 4th WK T
Succsess Group Invoice | bar: Sep-20 3rd WK T to Sep-20 3rd WK W; Sep-20 4th WK T
Offline Pay | bar: Sep-20 3rd WK M; Sep-20 3rd WK F; Sep-20 4th WK T to Sep-20 4th WK W
Update Local Pick Up | bar: Sep-20 3rd WK T; Sep-20 3rd WK F to Sep-20 4th WK M
Insert Shipping Check Out | bar: Sep-20 3rd WK W; Sep-20 3rd WK F to Sep-20 4th WK M
Contact Seller | bar: Sep-20 3rd WK T to Sep-20 4th WK T
Request Contact Seller | bar: Sep-20 4th WK T to Sep-20 4th WK T
Remove All Shipping New Wholesale | bar: Sep-20 4th WK T to Sep-20 4th WK F
Get Mulitple Print Lists | bar: Sep-20 4th WK T
Check Invoice | bar: Sep-20 4th WK T
Get Rate | bar: Sep-20 4th WK T to Sep-20 4th WK F
Change Password | bar: Sep-20 4th WK T
SliBuy PayPal Success | bar: Sep-20 4th WK T; Sep-20 4th WK T to Sep-20 4th WK F
Paypal Verification | bar: Sep-20 4th WK T
Paypal Notification | bar: Sep-20 4th WK T to Sep-20 4th WK F
Cancel SDK | bar: Sep-20 4th WK M to Sep-20 4th WK W
Success Paypal Sdk | bar: Sep-20 4th WK W to Sep-20 4th WK T
Spare Parts 3.0 | bar: Sep-20 4th WK F
Success SDK | bar: Sep-20 4th WK F
SliBuy Transaction | bar: Sep-20 4th WK F
SliBuy Transaction Payment | bar: Sep-20 4th WK F
New SliBuy Transaction Payment | bar: Sep-20 4th WK F
Cancel Apply Credits | bar: Sep-20 4th WK W to Sep-20 4th WK F
New Check Invoice Checkout | bar: Oct-20 1st WK M to Oct-20 1st WK T
My Bids Search | bar: Oct-20 1st WK T
Split Bid Won | bar: Oct-20 1st WK T
Split Bid Lost | bar: Oct-20 1st WK T to Oct-20 1st WK T
Update FCM | bar: Oct-20 1st WK M; Oct-20 1st WK W; Oct-20 1st WK F to Oct-20 2nd WK M
Cashout | bar: Oct-20 2nd WK M
Upload Images | bar: Oct-20 1st WK W to Oct-20 2nd WK M
Seller Post Project Live | bar: Oct-20 2nd WK M
Seller Post Project Live 2 | bar: Oct-20 2nd WK M to Oct-20 2nd WK W
Update Project Live | bar: Oct-20 2nd WK W
Update Project Live Old | bar: Oct-20 2nd WK W
Remove Shipping Checkout Admin | bar: Oct-20 2nd WK M to Oct-20 2nd WK W
Remove Product Details | bar: Oct-20 2nd WK M; Oct-20 2nd WK T to Oct-20 2nd WK F
USPS | bar: Oct-20 2nd WK M; Oct-20 2nd WK T
Tax ConsulataionQ | bar: Oct-20 2nd WK M; Oct-20 2nd WK T
Update User Profile | bar: Oct-20 2nd WK T to Oct-20 2nd WK T
Update User Personal Details | bar: Oct-20 2nd WK W
Get Store Details | bar: Oct-20 2nd WK W
Update Buy Now Details | bar: Oct-20 2nd WK W; Oct-20 2nd WK F
Update Project Details | bar: Oct-20 2nd WK M to Oct-20 2nd WK W; Oct-20 2nd WK F
Membership Renewal | bar: Oct-20 2nd WK W to Oct-20 2nd WK F
Spare Parts 4.0 | bar: Oct-20 2nd WK W
Update User Details | bar: Oct-20 2nd WK W
Get Product Details Farm | bar: Oct-20 2nd WK W to Oct-20 3rd WK W
Get Lots | bar: Oct-20 3rd WK T to Oct-20 3rd WK W
Get Sub Lots | bar: Oct-20 3rd WK T
Quickbook Expoort Customers | bar: Oct-20 2nd WK T to Oct-20 2nd WK F; Oct-20 3rd WK T to Oct-20 3rd WK W
Mobile confirm Buy | bar: Oct-20 2nd WK T to Oct-20 2nd WK W
Add To Cart | bar: Oct-20 2nd WK F
Update Card | bar: Oct-20 2nd WK F
Remove From Cart | bar: Oct-20 2nd WK W; Oct-20 2nd WK F
Get Buyer Cart | bar: Oct-20 2nd WK W to Oct-20 3rd WK T
Get My Communities | bar: Oct-20 3rd WK M; Oct-20 3rd WK W
Get All Communities | bar: Oct-20 3rd WK M; Oct-20 3rd WK T
View Community | bar: Oct-20 3rd WK M
Save Processor | bar: Oct-20 2nd WK W to Oct-20 3rd WK M; Oct-20 3rd WK W
Get Action Center | bar: Oct-20 3rd WK M; Oct-20 3rd WK W
Get Track Status | bar: Oct-20 3rd WK M to Oct-20 3rd WK W
Update Processor Track | bar: Oct-20 3rd WK W
Update Processor Acceptance Status | bar: Oct-20 3rd WK W to Oct-20 3rd WK F
Proccesor Preference | bar: Oct-20 3rd WK M to Oct-20 3rd WK W; Oct-20 3rd WK F
Get Proccesor Preference | bar: Oct-20 3rd WK W; Oct-20 3rd WK F
Delete Proccesor Preference | bar: Oct-20 3rd WK W; Oct-20 3rd WK F
Create Drop Off | bar: Oct-20 3rd WK W to Oct-20 3rd WK T
Get Processor Calender | bar: Oct-20 3rd WK T to Oct-20 3rd WK F
Remove Event | bar: Oct-20 3rd WK F
Get Processors List | bar: Oct-20 3rd WK T to Oct-20 3rd WK F
Get User Details | bar: Oct-20 3rd WK W to Oct-20 3rd WK T
Spare Parts 5.0 | bar: Oct-20 3rd WK T to Oct-20 4th WK M
Get Role | bar: Oct-20 4th WK M
Remove Wathchlist | bar: Oct-20 4th WK M
Insert Messages | bar: Oct-20 4th WK M
Insert Messages 2 | bar: Oct-20 4th WK M to Oct-20 4th WK T
Get Chat History 2 | bar: Oct-20 4th WK T
Insert Blog Post | bar: Oct-20 4th WK T
List Blog Pagination | bar: Oct-20 4th WK T
Get Blog Post | bar: Oct-20 4th WK T
List Buyer Pagintaion | bar: Oct-20 4th WK T
List Buyer | bar: Oct-20 4th WK T
Get Chat History | bar: Oct-20 4th WK T
Get SYP Products | bar: Oct-20 4th WK T to Oct-20 4th WK F
Update SYP Products | bar: Oct-20 4th WK M; Oct-20 4th WK T to Oct-20 4th WK F
Add New Discussion | bar: Oct-20 4th WK T
Show All Discussion | bar: Oct-20 4th WK W
Show All Discussion Search | bar: Oct-20 4th WK W to Oct-20 4th WK F
Show All Community Member | bar: Oct-20 4th WK W
Show All Community Search | bar: Oct-20 4th WK W
Show All Community | bar: Oct-20 4th WK W
Add Watch List | bar: Oct-20 4th WK M to Oct-20 4th WK T
Show Favorite Farms | bar: Oct-20 4th WK M; Oct-20 4th WK W
Remove Favorite Farm | bar: Oct-20 4th WK M; Oct-20 4th WK T
Show Transaction | bar: Oct-20 4th WK M
Show Watch List | bar: Oct-20 4th WK M; Oct-20 4th WK W
Add Favorite Farms | bar: Oct-20 4th WK M; Oct-20 4th WK W
Give Ratings | bar: Oct-20 4th WK M to Oct-20 4th WK W
Spare Parts 6.0 | bar: Oct-20 4th WK W
Show Past Purchaeses | bar: Oct-20 4th WK W to Oct-20 4th WK F
Search Without Login | bar: Oct-20 4th WK M to Oct-20 4th WK W; Oct-20 4th WK F
Update Zift Pay Token | bar: Oct-20 4th WK W; Oct-20 4th WK F
Show Event Content | bar: Oct-20 4th WK W; Oct-20 4th WK F
Show Static Content | bar: Oct-20 4th WK W to Oct-20 4th WK T
Get Tiles Count | bar: Oct-20 4th WK T to Oct-20 4th WK F
Pro Accept Reject List | bar: Oct-20 4th WK F
Show Seller Transaction | bar: Oct-20 4th WK W to Oct-20 4th WK T
Show Available Slot | bar: Oct-20 4th WK M; Oct-20 4th WK W
Show Queue Items | bar: Oct-20 4th WK M; Oct-20 4th WK W
After Processor Pay | bar: Oct-20 4th WK M to Oct-20 4th WK W
Buy Now Product | bar: Oct-20 4th WK W
Change Product Status | bar: Oct-20 4th WK W to Oct-20 4th WK F
Get Seller Products | bar: Oct-20 4th WK M to Oct-20 4th WK W; Oct-20 4th WK F
Get Seller Sold Products | bar: Oct-20 4th WK W; Oct-20 4th WK F
Change Message Status | bar: Oct-20 4th WK W; Oct-20 4th WK F
Auction Search | bar: Oct-20 4th WK W to Oct-20 4th WK T
Get Seller Auctions
Approve Hatechery Buyer | bar: Nov-20 1st WK M
Approve Unapproved Hatechery Buyer | bar: Nov-20 1st WK M
Unpaid Admin Invoice Algo | bar: Nov-20 1st WK M; Nov-20 1st WK W
Send Selling Form | bar: Nov-20 1st WK M
Send Career Form | bar: Nov-20 1st WK M
Get Invoice Details | bar: Nov-20 1st WK T to Nov-20 1st WK W
Get Haulier
Update Pickup | bar: Nov-20 1st WK T to Nov-20 1st WK W
Update Delivery
Spare Parts 7.0 | bar: Nov-20 1st WK M to Nov-20 1st WK T
Get Address Details | bar: Nov-20 1st WK M
Add New Address | bar: Nov-20 1st WK M
Set Default Address | bar: Nov-20 1st WK M
Get User Wallet Details | bar: Nov-20 1st WK M to Nov-20 1st WK T
Get Parent Category | bar: Nov-20 1st WK M
Get Parent Filter | bar: Nov-20 1st WK M; Nov-20 1st WK W to Nov-20 1st WK T
Get Sub Categoryr
Get Sub Filter | bar: Nov-20 1st WK M to Nov-20 1st WK W
Bid Increments | bar: Nov-20 1st WK M
Vehicle Post Api V1 | bar: Nov-20 1st WK M
Lot Search | bar: Nov-20 1st WK W
Delete Blog Search | bar: Nov-20 1st WK M; Nov-20 1st WK W
Update Card | bar: Nov-20 1st WK M to Nov-20 1st WK W
Get LA Sellers | bar: Nov-20 1st WK W
Site Map | bar: Nov-20 1st WK W
Send Mail One Hour Old | bar: Nov-20 1st WK W
Send Mail One Hour | bar: Nov-20 1st WK W to Nov-20 1st WK T
Auto Invoice Label | bar: Nov-20 1st WK F
Insert Product Viewed | bar: Nov-20 1st WK F
Get Seller Products Viewed | bar: Nov-20 1st WK F
Get Buyers Guide Of Product | bar: Nov-20 1st WK F
Get FAQ Of Product | bar: Nov-20 2nd WK M
Verify Login | bar: Nov-20 2nd WK T
Verify OTP | bar: Nov-20 2nd WK W to Nov-20 2nd WK F
Insert User Proposals | bar: Nov-20 2nd WK F
Get User Proposals | bar: Nov-20 2nd WK F
Spare Parts 8.0 | bar: Nov-20 2nd WK F
Update Bid Deposit | bar: Nov-20 2nd WK F to Nov-20 3rd WK W; Nov-20 4th WK M to Nov-20 4th WK T
Create Coupon Code | bar: Nov-20 3rd WK W to Nov-20 4th WK T
Get User Coupons | bar: Nov-20 3rd WK W; Nov-20 4th WK T; Nov-20 4th WK T to Nov-20 4th WK F
Register Bid Deposit | bar: Nov-20 3rd WK M to Nov-20 3rd WK W; Nov-20 4th WK T
Get OTP Register | bar: Nov-20 4th WK T
Insert User Posted Product | bar: Nov-20 4th WK W to Nov-20 4th WK F
Satellite Sms | bar: Dec-20 1st WK M; Dec-20 1st WK W to Dec-20 1st WK F
Check Password Changed | bar: Dec-20 1st WK M; Dec-20 2nd WK M
List Sub Admins | bar: Dec-20 1st WK M to Dec-20 1st WK W; Dec-20 2nd WK M to Dec-20 2nd WK T
Reverse API | bar: Dec-20 1st WK W; Dec-20 2nd WK T; Dec-20 2nd WK T
Penny API | bar: Dec-20 1st WK W; Dec-20 2nd WK T; Dec-20 3rd WK M
Payment API [Stripe] | bar: Dec-20 1st WK W; Dec-20 2nd WK T; Dec-20 3rd WK M
Testing and Delivery | bar: Dec-20 1st WK T to Dec-20 1st WK T; Dec-20 2nd WK T to Dec-20 2nd WK W; Dec-20 3rd WK M; Dec-20 3rd WK W
Manual Testing | bar: Dec-20 1st WK W to Dec-20 2nd WK M; Dec-20 2nd WK W to Dec-20 3rd WK T; Dec-20 4th WK T
Mass Testing | bar: Dec-20 1st WK T; Dec-20 2nd WK T; Dec-20 3rd WK T; Dec-20 4th WK T to Dec-20 4th WK F
Automation Testing | bar: Dec-20 1st WK W to Dec-20 1st WK T; Dec-20 2nd WK M to Dec-20 2nd WK T; Dec-20 3rd WK T to Dec-20 4th WK T
Load Testing | bar: Dec-20 1st WK W; Dec-20 2nd WK T; Dec-20 3rd WK W; Dec-20 4th WK T; Dec-20 4th WK T
Penetration /Security Testing | bar: Dec-20 1st WK W; Dec-20 2nd WK T; Dec-20 3rd WK W; Dec-20 4th WK T to Dec-20 4th WK T
Beta Testing & Delivery | bar: Dec-20 1st WK W; Dec-20 3rd WK W

## Large_Custom -- 2020 Release
LARGE- FEATURE LIST Release JUNE 2019 - DECEMBER 2020
PROJECT TITLE : Large Custom Features
PROJECT MANAGER : Srikanth Baskaran
COMPANY NAME : AuctionSoftware
| June- 20 1st WK |  |  |  |  | June- 20 2nd WK |  |  |  |  | June- 20 3rd WK |  |  |  |  | June- 20 4th WK |  |  |  |  | July -20 1st Week |  |  |  |  | July -20 2nd Week |  |  |  |  | July -20 3rd Week |  |  |  |  | July -20 4th Week |  |  |  |  | Aug -20 1st Week |  |  |  |  | Aug -20 2nd Week |  |  |  |  | Aug -20 3rd Week |  |  |  |  | Aug -20 4th Week |  |  |  |  | Sept -20 1st Week |  |  |  |  | Sept -20 2nd Week |  |  |  |  | Sept -20 3rd Week |  |  |  |  | Sept -20 4th Week |  |  |  |  | Oct -20 1st Week |  |  |  |  | Oct -20 2nd Week |  |  |  |  | Oct -20 3rd Week |  |  |  |  | Oct -20 4th Week |  |  |  |  | Nov -20 1st Week |  |  |  |  | Nov -20 2nd Week |  |  |  |  | Nov -20 3rd Week |  |  |  |  | Nov -20 4th Week |  |  |  |  | Dec -20 1st Week |  |  |  |  | Dec -20 2nd Week |  |  |  |  | Dec-20 3rd Week |  |  |  |  | Dec -20 4th Week
| M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
Authentication | bar: June- 20 1st WK M to June- 20 1st WK F
Registration | bar: June- 20 1st WK M
Social media signup/ Signin | bar: June- 20 1st WK M
Email verification | bar: June- 20 1st WK T to June- 20 1st WK W
Login | bar: June- 20 1st WK T
Forgot password | bar: June- 20 1st WK W to June- 20 1st WK T
Homepage | bar: June- 20 1st WK F
Search | bar: June- 20 2nd WK M to June- 20 3rd WK T
Search by Filters | bar: June- 20 2nd WK M; June- 20 3rd WK M
Product View without Login | bar: June- 20 2nd WK M; June- 20 3rd WK M; June- 20 4th WK M to June- 20 4th WK T
Product View with Login | bar: June- 20 4th WK M
Add Product To Watchlist | bar: June- 20 2nd WK T to June- 20 2nd WK W; June- 20 3rd WK T to June- 20 3rd WK W; June- 20 4th WK W to June- 20 4th WK T
Remove Product From Watchlist | bar: June- 20 2nd WK W to June- 20 2nd WK T; June- 20 3rd WK W to June- 20 3rd WK T; June- 20 4th WK M to June- 20 4th WK T
Special Events | bar: June- 20 2nd WK F; June- 20 3rd WK F; June- 20 4th WK T to June- 20 4th WK F
Profile | bar: July -20 1st Week M to July -20 1st Week F
Get Profile Details | bar: July -20 1st Week T to July -20 1st Week W
Update Profile | bar: July -20 1st Week T to July -20 1st Week F
Change Password | bar: July -20 1st Week T to July -20 1st Week W
Notification | bar: July -20 1st Week W to July -20 1st Week T
Email Notifications | bar: July -20 1st Week F; July -20 2nd Week W
SMS Notifications | bar: July -20 2nd Week M to July -20 2nd Week F
My Auctions | bar: July -20 2nd Week T; July -20 2nd Week T
All | bar: July -20 2nd Week W
Winning | bar: July -20 2nd Week W to July -20 2nd Week T; July -20 3rd Week M; July -20 3rd Week W
Outbid | bar: July -20 2nd Week T to July -20 2nd Week W; July -20 3rd Week M to July -20 3rd Week W; July -20 4th Week M to July -20 4th Week T
Won | bar: July -20 2nd Week F to July -20 3rd Week W; July -20 4th Week M to July -20 4th Week T
Watchlist | bar: July -20 3rd Week T; July -20 4th Week M to July -20 4th Week T
View Watclist | bar: July -20 3rd Week W to July -20 3rd Week F; July -20 4th Week T; July -20 4th Week F
Add Product To Watchlist | bar: July -20 3rd Week T to July -20 3rd Week F; July -20 4th Week W to July -20 4th Week F
Remove Product From Watchlist | bar: July -20 4th Week M; July -20 4th Week W to July -20 4th Week T
Bidding | bar: Aug -20 1st Week M to Aug -20 1st Week T
Bid Validation | bar: Aug -20 1st Week T to Aug -20 1st Week W
Bid Increment | bar: Aug -20 1st Week M to Aug -20 1st Week T; Aug -20 1st Week T; Aug -20 2nd Week M to Aug -20 2nd Week T
Bid History | bar: Aug -20 1st Week T; Aug -20 2nd Week T to Aug -20 2nd Week W; Aug -20 3rd Week M
Awarding | bar: Aug -20 1st Week T to Aug -20 2nd Week T; Aug -20 3rd Week T to Aug -20 3rd Week W
Cart | bar: Aug -20 1st Week T to Aug -20 1st Week F; Aug -20 2nd Week W to Aug -20 2nd Week T; Aug -20 3rd Week W to Aug -20 3rd Week F
Add to cart | bar: Aug -20 3rd Week F; Aug -20 4th Week T
Remove to cart | bar: Aug -20 3rd Week F; Aug -20 4th Week W
View cart | bar: Aug -20 4th Week T to Aug -20 4th Week F
Appointment | bar: Aug -20 4th Week T to Aug -20 4th Week F
Cart
Return Cart | bar: Dec -20 1st Week M to Dec -20 1st Week T
Return Invoice | bar: Dec -20 1st Week T to Dec -20 1st Week T
Emails Triggers | bar: Dec -20 1st Week W to Dec -20 2nd Week T
Messages Triggers | bar: Dec -20 1st Week W to Dec -20 1st Week T; Dec -20 2nd Week T to Dec -20 2nd Week F
Checkout | bar: Sept -20 1st Week M to Sept -20 1st Week T; Dec -20 2nd Week W to Dec -20 2nd Week F
Add Billing Address | bar: Sept -20 1st Week T; Sept -20 1st Week T; Dec -20 2nd Week W to Dec -20 2nd Week T
Single card payment | bar: Sept -20 1st Week T to Sept -20 1st Week F; Sept -20 2nd Week T to Sept -20 2nd Week W
Double card Payment | bar: Sept -20 1st Week T to Sept -20 2nd Week M; Sept -20 2nd Week W
Invoice | bar: Sept -20 2nd Week W to Sept -20 2nd Week T; Sept -20 3rd Week T to Sept -20 3rd Week W
View Invoice | bar: Sept -20 2nd Week T to Sept -20 3rd Week M; Sept -20 3rd Week W; Sept -20 4th Week W to Sept -20 4th Week F
Return | bar: Sept -20 3rd Week W; Sept -20 4th Week M; Sept -20 4th Week W to Sept -20 4th Week F
Return Invoice | bar: Sept -20 3rd Week T; Sept -20 4th Week M; Sept -20 4th Week T
Admin | bar: Sept -20 4th Week M to Sept -20 4th Week T
Dashboard | bar: Oct -20 1st Week M to Oct -20 1st Week T
Active Items | bar: Oct -20 1st Week M
Draft Items | bar: Oct -20 1st Week M
Sold Items | bar: Oct -20 1st Week T to Oct -20 1st Week W
Unsold Items | bar: Oct -20 1st Week T
Auction lots | bar: Oct -20 1st Week W to Oct -20 1st Week F
Listings
Active | bar: Oct -20 2nd Week M to Oct -20 2nd Week T
Sold | bar: Oct -20 2nd Week M
Unsold | bar: Oct -20 2nd Week M; Oct -20 2nd Week T to Oct -20 2nd Week F
Draft | bar: Oct -20 2nd Week F
User | bar: Oct -20 2nd Week T to Oct -20 2nd Week W; Oct -20 2nd Week F
All | bar: Oct -20 2nd Week W to Oct -20 3rd Week T; Oct -20 4th Week M; Oct -20 4th Week T
Active | bar: Oct -20 3rd Week M; Oct -20 4th Week T to Oct -20 4th Week F
Deactivated | bar: Oct -20 3rd Week M; Oct -20 3rd Week T; Oct -20 4th Week T to Oct -20 4th Week W; Oct -20 4th Week F
Invoice | bar: Oct -20 4th Week F
Paid | bar: Oct -20 3rd Week T to Oct -20 3rd Week W
Unpaid | bar: Oct -20 3rd Week M; Oct -20 3rd Week T to Oct -20 3rd Week F; Oct -20 4th Week W to Oct -20 4th Week T
Return | bar: Oct -20 3rd Week M to Oct -20 3rd Week F; Oct -20 4th Week W to Oct -20 4th Week F; Dec -20 2nd Week M; Dec -20 2nd Week F
Pending | bar: Dec -20 2nd Week T to Dec -20 2nd Week T; Dec-20 3rd Week M to Dec-20 3rd Week T
Completed | bar: Dec -20 2nd Week T to Dec -20 2nd Week T; Dec-20 3rd Week T to Dec-20 3rd Week T; Dec -20 4th Week W
Transactions | bar: Nov -20 1st Week M to Nov -20 1st Week T; Dec-20 3rd Week W to Dec -20 4th Week T; Dec -20 4th Week T to Dec -20 4th Week F
Payment | bar: Nov -20 1st Week M to Nov -20 1st Week T; Dec-20 3rd Week W to Dec-20 3rd Week T; Dec -20 4th Week W
Refund | bar: Nov -20 1st Week T; Nov -20 2nd Week M to Nov -20 2nd Week T; Dec -20 4th Week M; Dec -20 4th Week W to Dec -20 4th Week F
Employee | bar: Nov -20 1st Week W to Nov -20 1st Week T; Nov -20 2nd Week M to Nov -20 2nd Week T; Dec -20 4th Week W to Dec -20 4th Week F
All | bar: Nov -20 1st Week F; Nov -20 2nd Week T; Nov -20 3rd Week T to Nov -20 3rd Week W
Report | bar: Nov -20 2nd Week W to Nov -20 2nd Week T; Nov -20 3rd Week T to Nov -20 3rd Week F
Communications | bar: Nov -20 2nd Week F; Nov -20 3rd Week W; Nov -20 4th Week T
Email template | bar: Nov -20 2nd Week T; Nov -20 3rd Week T to Nov -20 3rd Week F; Nov -20 4th Week T to Nov -20 4th Week T
SMS Template | bar: Nov -20 2nd Week T; Nov -20 3rd Week T; Nov -20 4th Week M to Nov -20 4th Week T
Email Logs | bar: Nov -20 2nd Week T; Nov -20 4th Week W to Nov -20 4th Week T
Settings | bar: Nov -20 4th Week F
Static Pages | bar: Nov -20 4th Week T to Nov -20 4th Week W
General Settings | bar: Nov -20 4th Week M; Nov -20 4th Week T to Nov -20 4th Week F
Testing and Delivery | bar: Nov -20 1st Week M to Nov -20 2nd Week W; Nov -20 3rd Week M to Nov -20 3rd Week T; Dec -20 1st Week T to Dec -20 1st Week T
Manual Testing | bar: Oct -20 3rd Week M to Oct -20 3rd Week F; Oct -20 4th Week T to Oct -20 4th Week T; Nov -20 2nd Week M to Nov -20 2nd Week W; Nov -20 3rd Week M to Nov -20 3rd Week T; Nov -20 4th Week M to Nov -20 4th Week F
Mass Testing | bar: Oct -20 3rd Week W; Nov -20 2nd Week W to Nov -20 2nd Week F
Automation Testing | bar: Oct -20 4th Week F; Nov -20 2nd Week W to Nov -20 2nd Week F; Nov -20 3rd Week T to Nov -20 3rd Week F; Dec -20 1st Week M to Dec -20 1st Week T; Dec -20 2nd Week M to Dec -20 2nd Week T
Load Testing | bar: Nov -20 4th Week M to Nov -20 4th Week T; Dec -20 1st Week W to Dec -20 2nd Week T; Dec -20 2nd Week T to Dec-20 3rd Week F; Dec -20 4th Week T to Dec -20 4th Week F
Penetration /Security Testing | bar: Dec -20 1st Week W to Dec -20 1st Week F; Dec -20 2nd Week W; Dec -20 4th Week M to Dec -20 4th Week F
Beta Testing & Delivery | bar: Dec -20 1st Week T to Dec -20 1st Week F; Dec-20 3rd Week W to Dec -20 4th Week F

## Product_RoadMap -- 2021
PRODUCT ROAD MAP -- 2021
PROJECT TITLE : Product_Road_Map
PROJECT MANAGER : AS Product Manager
COMPANY NAME : AuctionSoftware
| Jan-21 1st WK |  |  |  |  | Jan-21 2nd WK |  |  |  |  | Jan-21 3rd WK |  |  |  |  | Jan-21 4th WK |  |  |  |  | Feb-21 1st WK |  |  |  |  | Feb-21 2nd WK |  |  |  |  | Feb-21 3rd WK |  |  |  |  | Feb-21 4th WK |  |  |  |  | March-21 1st WK |  |  |  |  | March-21 2nd WK |  |  |  |  | March-21 3rd WK |  |  |  |  | March-21 4th WK |  |  |  |  | April-21 1st WK |  |  |  |  | April-21 2nd WK |  |  |  |  | April-21 3rd WK |  |  |  |  | April-21 4th WK |  |  |  |  | May-21 1st WK |  |  |  |  | May-21 2nd WK |  |  |  |  | May-21 3rd WK |  |  |  |  | May-21 4th WK |  |  |  |  | June-21 1st WK |  |  |  |  | Jne-21 2nd WK |  |  |  |  | June-21 3rd WK |  |  |  |  | June-21 4th WK |  |  |  |  | July-21 1st WK |  |  |  |  | July-21 2nd WK |  |  |  |  | July-21 3rd WK |  |  |  |  | July-21 4th WK |  |  |  |  | Aug-21 1st WK |  |  |  |  | Aug-21 2nd WK |  |  |  |  | Aug-21 3rd WK |  |  |  |  | Aug-21 4th WK |  |  |  |  | Sep-21 1st WK |  |  |  |  | Sep-21 2nd WK |  |  |  |  | Sep-21 3rd WK |  |  |  |  | Sep-21 4th WK |  |  |  |  | Oct-21 1st WK |  |  |  |  | Oct-21 2nd WK |  |  |  |  | Oct-21 3rd WK |  |  |  |  | Oct-21 4th WK |  |  |  |  | Nov-21 1st WK |  |  |  |  | Nov-21 2nd WK |  |  |  |  | Nov-21 3rd WK |  |  |  |  | Nov-21 4th WK |  |  |  |  | Dec-21 1st WK |  |  |  |  | Dec-21 2nd WK |  |  |  |  | Dec-21 3rd WK |  |  |  |  | Dec-21 4th WK
| M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
Small_SAAS | bar: Jan-21 1st WK M to Jan-21 1st WK F; March-21 1st WK M to March-21 1st WK T; April-21 1st WK M
QR scan Code | bar: Jan-21 1st WK T; Jan-21 1st WK T; March-21 1st WK M to March-21 1st WK T
Reseller APP | bar: Jan-21 1st WK T to Jan-21 1st WK F; Jan-21 2nd WK T to Jan-21 2nd WK W; March-21 1st WK W to March-21 2nd WK T
Fair market value | bar: Jan-21 1st WK T to Jan-21 2nd WK M; Jan-21 2nd WK W; March-21 2nd WK T to March-21 3rd WK M
Auto calculation of basket fair market value | bar: Jan-21 2nd WK W to Jan-21 2nd WK T; Jan-21 3rd WK T to Jan-21 3rd WK W; March-21 2nd WK T to March-21 2nd WK W; March-21 3rd WK T to March-21 3rd WK F
IOS and Android Apps | bar: Jan-21 2nd WK T to Jan-21 3rd WK M; Jan-21 3rd WK W; Jan-21 4th WK W to Feb-21 1st WK T; March-21 3rd WK T to March-21 3rd WK W
10 more standard Themes | bar: Jan-21 3rd WK W; Jan-21 4th WK M; Jan-21 4th WK W to Feb-21 1st WK M; March-21 1st WK M
Medium_Control Hub | bar: Jan-21 3rd WK T to Jan-21 4th WK M; Jan-21 4th WK T; Feb-21 1st WK M; Feb-21 3rd WK M to Feb-21 3rd WK T; Feb-21 4th WK M; Feb-21 4th WK T
Deposit and Wallet | bar: Jan-21 4th WK M to Jan-21 4th WK T; Feb-21 1st WK T to Feb-21 1st WK W; Feb-21 3rd WK M; Feb-21 4th WK T to Feb-21 4th WK F
Partial Payment | bar: Feb-21 1st WK T; Feb-21 3rd WK M; Feb-21 3rd WK T; Feb-21 4th WK T to Feb-21 4th WK W; Feb-21 4th WK F
Referal and Earn | bar: Feb-21 1st WK W to Feb-21 1st WK F; Feb-21 4th WK F
Facebook and Linked In Login | bar: Feb-21 3rd WK T to Feb-21 3rd WK W
RealEstate | bar: Feb-21 2nd WK M to Feb-21 2nd WK T; Feb-21 3rd WK M; Feb-21 3rd WK T to Feb-21 3rd WK F; Feb-21 4th WK W to Feb-21 4th WK T
Tax calculation | bar: Feb-21 2nd WK M; Feb-21 3rd WK M to Feb-21 3rd WK F; Feb-21 4th WK W to Feb-21 4th WK F; March-21 3rd WK M; March-21 3rd WK W
Reserve Price void for FIrst Bidder | bar: Feb-21 2nd WK M; Feb-21 2nd WK T to Feb-21 2nd WK F; March-21 3rd WK M to March-21 3rd WK W; March-21 4th WK M to March-21 4th WK T
Seller Payout | bar: Feb-21 2nd WK F; March-21 3rd WK M to March-21 3rd WK W; March-21 4th WK M to March-21 4th WK T
4 Standard Themes | bar: Feb-21 2nd WK T to Feb-21 2nd WK W; Feb-21 2nd WK F; March-21 3rd WK T; March-21 4th WK M to March-21 4th WK T; April-21 1st WK M to April-21 1st WK W
Large_Custom | bar: March-21 4th WK M; March-21 4th WK W to March-21 4th WK T; April-21 1st WK W; April-21 2nd WK M to April-21 2nd WK W; July-21 1st WK T to July-21 1st WK F
Language Manager | bar: April-21 1st WK T to April-21 1st WK F; April-21 2nd WK T to April-21 2nd WK W; July-21 1st WK T to July-21 1st WK W
Payment by Cash / Credit | bar: April-21 2nd WK W to April-21 2nd WK F; July-21 1st WK W to July-21 1st WK T
Admin - Dynamic Bid Increment | bar: April-21 2nd WK F to April-21 3rd WK T; April-21 3rd WK T to April-21 3rd WK F; July-21 1st WK F; July-21 2nd WK W
Admin - Staggered and Extended Bidding | bar: April-21 3rd WK T to April-21 3rd WK T; July-21 2nd WK M to July-21 2nd WK F
Live Streaming Auctions | bar: April-21 4th WK M to April-21 4th WK T; April-21 4th WK T to April-21 4th WK F; July-21 2nd WK T; July-21 2nd WK T
Admin - Auctioneer | bar: April-21 4th WK T to April-21 4th WK T; July-21 2nd WK W
Admin Manage Meta-Tags | bar: July-21 2nd WK W to July-21 2nd WK T; July-21 3rd WK M; July-21 3rd WK W
5 More Front end Themes | bar: May-21 1st WK T to May-21 1st WK F; July-21 3rd WK T; July-21 4th WK M to July-21 4th WK T; Sep-21 1st WK T; Sep-21 1st WK T
More Features in ControlHub | bar: May-21 1st WK F to June-21 4th WK F; July-21 3rd WK W to July-21 3rd WK F; July-21 4th WK T; July-21 4th WK F to Aug-21 1st WK T; Sep-21 1st WK T to Sep-21 1st WK F; Sep-21 2nd WK T to Sep-21 2nd WK W
Testing and Delivery | bar: July-21 3rd WK T to July-21 3rd WK F; July-21 4th WK W to July-21 4th WK F; Aug-21 1st WK T to Aug-21 1st WK W; Sep-21 1st WK T to Sep-21 2nd WK M; Sep-21 2nd WK W
Manual Testing | bar: July-21 4th WK M; July-21 4th WK W to July-21 4th WK T; Aug-21 1st WK M to Aug-21 1st WK T; Aug-21 1st WK T; Aug-21 2nd WK M to Aug-21 2nd WK T; Sep-21 2nd WK W to Sep-21 2nd WK T; Sep-21 3rd WK T to Sep-21 3rd WK W
Mass Testing | bar: Aug-21 1st WK T; Aug-21 2nd WK T to Aug-21 2nd WK W; Aug-21 3rd WK M; Sep-21 2nd WK T to Sep-21 3rd WK M; Sep-21 3rd WK W; Sep-21 4th WK W to Sep-21 4th WK F
Automation Testing | bar: Aug-21 1st WK T to Aug-21 2nd WK T; Aug-21 3rd WK T to Aug-21 3rd WK W; Sep-21 3rd WK W; Sep-21 4th WK M; Sep-21 4th WK W to Sep-21 4th WK F
Load Testing | bar: Aug-21 1st WK T to Aug-21 1st WK F; Aug-21 2nd WK W to Aug-21 2nd WK T; Aug-21 3rd WK W to Aug-21 3rd WK F; Sep-21 3rd WK T; Sep-21 4th WK M; Sep-21 4th WK T
Penetration /Security Testing | bar: Aug-21 3rd WK F; Aug-21 4th WK T; Sep-21 4th WK M to Sep-21 4th WK T
Beta Testing & Delivery | bar: Aug-21 3rd WK F; Aug-21 4th WK W